## Sheet1
Activities	Start	Hours	Target	Status	KEY	01/27/17	02/03/17	02/10/17	02/17/17	02/24/17	03/03/17	03/10/17	03/17/17	03/24/17	03/31/17	04/07/17	04/14/17	04/21/17	04/28/17	05/05/17	05/12/17	<-- week's end
					ON TRACK
REQUIRED					MISSED
DEPRECIATED					NOT ON TRACK
					STRETCH GOALS
					COMPLETE
					SCHEDULED
					PRECOMPLETED
					URGENT	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	*
Concept & Requirements
Write mission statement	01/24/17	1	01/24/17
Goal Model	01/24/17	4	01/24/17
Setup git repository	01/24/17	1	01/24/17
Context Model	01/24/17	4	01/24/17
Update Waffle & Gantt Chart	01/25/17	8	02/01/17
Setup Waffle & Gantt Chart
Document Stakeholders	01/24/17	1	01/24/17
Initial Formal Requirements Document	01/24/17	4	02/01/17
Update Formal Requirements Document
Update Concept & Requirements Documents
Context Model of UI	01/28/17	3	02/03/17
Goal Model of UI	01/28/17	3	02/03/17
Define goal completeness criteria	02/01/17	1	02/03/17
Redo Goals model			02/03/17

Design
Sequence Diagrams
Detect Human face in image	02/03/17	3	02/10/17	X					X
Detect Human form in image	02/03/17	3	02/10/17	X					X
Detect Human in video	02/11/17	3	02/17/17
Detect Motion in video	02/11/17	4	02/17/17
Identify Moving Human in video	02/11/17	4	02/17/17
Determine if intruder detected	02/11/17	4	02/17/17
Record images when intruder detected		3
Images available to email		3
Send email with image		3
UI client with status and schedule editing		3
UI service
UI secure connection
Scheduling Changes
Status Changes
System		3

UML Class Diagrams
Diagram CVDetectIntruder classes	01/27/17	3	02/03/17	X			X
Diagram UI tool classes		3		X							X	X

figure out open ssl or some security protocol		2
Research secure connection alternatives		3

Implementation

Install LAMP on Raspberry Pi	01/28/17	1	02/03/17
Install OS on Raspberry Pi	01/28/17	2	02/03/17
Install OpenCV on Raspberry Pi	01/28/17	4	02/03/17
Write Code
Detect Human face in image		4		X						X
Detect Human form in image		4		X						X
Detect Human in video		4
Detect Motion in video		4
Identify Moving Human in video
Determine if intruder detected		4
Record images when intruder detected		4
Images available to email		4
Send email with image		4
UI client with status and schedule editing
UI service		4
UI secure connection		4
Scheduling Changes
Status Changes
System		12

User Documentation
Installation manual
User manual

Evaluation (QA)
Unit Testing
Detect Human face in image		4		X							X
Detect Human form in image		4		X							X
Detect Human in video		4
Detect Motion in video		4
Identify Moving Human in video		4
Determine if intruder detected		4
Record images when intruder detected		4
Images available to email		4
Send email with image		4
UI client with status and schedule editing		4
UI service		4
UI secure connection		4
Scheduling Changes		4
Status Changes		4
System

Integration Testing
Determine if intruder present		4
UI – App communication		4

Systems Testing
Test OpenCV installation		1
Test Camera/OpenCV connection	02/11/17

QA Testing (Acceptance/Validation Testing)
Run 1000 intruder detection tests without error		8
Attempt to override UI – app security		8
Develop positive & negive pedestrian tests