## Sheet1
Activities	Start	Hours	Target	Status	KEY	01/27/17	02/03/17	02/10/17	02/17/17	02/24/17	03/03/17	03/10/17	03/17/17	03/24/17	03/31/17	04/07/17	04/14/17	04/21/17	04/28/17	05/05/17	05/12/17
					ON TRACK
					MISSED
					NOT ON TRACK
					STRETCH GOALS
					COMPLETE
					SCHEDULED
					URGENT	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
Concept & Requirements
Write mission statement	01/24/17	1	01/24/17
Goal Model	01/24/17	4	01/24/17
Setup git repository	01/24/17	1	01/24/17
Context Model	01/24/17	4	01/24/17
Update Waffle & Gantt Chart	01/25/17	8	02/01/17
Setup Waffle & Gantt Chart
Document Stakeholders	01/24/17	1	01/24/17
Initial Formal Requirements Document	01/24/17	4	02/01/17
Update Formal Requirements Document
Update Concept & Requirements Documents
Context Model of UI	01/28/17	3	02/03/17
Goal Model of UI	01/28/17	3	02/03/17
Goal Model for app security	02/03/17	3	02/17/17
Define goal completeness criteria	02/01/17	1	02/03/17
Redo Goals model

Design
Sequence Diagrams
Animate Object Detection		3
Distinguish between Animate/Non-Animate		3
Prepare & send message		3
User Statistics UI, model & controller	02/04/17	4
User System Setup UI, model & controller	02/04/17	4
User Controls UI, model & controller	02/04/17	4
Determine if intruder present		3
Capture Images		3
Identify human form in image		3
Identify Face in image		3
System		3
UML Class Diagrams
Diagram CVDetectIntruder classes		3
Diagram UI tool classes		3

Look for design patterns used by/in system	01/27/17	4	03/03/17

figure out open ssl or some security protocol		2

Implementation
Install OS on Raspberry Pi		2
Install OpenCV on Raspberry Pi		4
Write Code
Animate Object Detection		4
Distinguish between Animate/Non-Animate		4
Prepare & send message		4
User Statistics UI, model & controller		4
User System Setup UI, model & controller		4
User Controls UI, model & controller		4
Determine if intruder present		4
Capture Images		4
Identify human form in image		4
Identify Moving Face in image		4
System		12

User Documentation
Installation manual
User manual

Evaluation (QA)
Unit Testing
Animate Object Detection		4
Distinguish between Animate/Non-Animate		4
Prepare & send message		4
User Statistics UI, model & controller		4
User System Setup UI, model & controller		4
User Controls UI, model & controller		4
Determine if intruder present		4
Capture Images		4
Identify human form in image		4
Identify Face in image		4

Integration Testing
Determine if intruder present		4
UI – App communication		4

Systems Testing
Test OpenCV installation		1
Test Camera/OpenCV connection

QA Testing (Acceptance/Validation Testing)
Run 1000 intruder detection tests without error		8
Attempt to override UI – app security		8